## Sheet1
SL No. | Milestones/Deliverables/Tasks | Start | Finish | Revised Start | Revised Finish | % Complete | Resource | Status | Dependencies | Owner of the Dependencies | completion Date of Dependcies
1 | Pre-Implementation Workshop
Sub tasks | Identify the applications / app groups for Near Term Implementation
Project specific deep dive discussion/meetings
Finalize the tools needed for implementation
Finalize Platform (PCF, OnPrem, Cloud, Containers)
Establish RACI
Socialize DevOps Strategy
Identify and prioritize apps for QA Automation development.
Analyze existing regression suite and Test Cases
Access Request
Identify Stakeholders
Collect Documentation - Architecture Diagram, - SDLC Workflow, - Release governance process, - Volumetric details, - KPI
| Environment, Server provisioning Network setup, Security | ,
Finalize pilot
2 | Tool Integration
Setup and Configure Jira
Sub tasks | Pivotal Tracker and Jira Integration
Git Integration with CI Tool (Team City/Jenkins)
Teamcity/Jenkins Setup
Jenkins Master-Slave Architecture setup
Jenkins Plugin installation and configuration
Junit integration with Jenkins
Jenkins Integration with Maven
Jenkins Integration with Gradle
Sonarqube installation and setup
Sonarqube integration with Jenkins
Setup Nexus/Artifactory
Nexus/Artifactory integration with CI Tool (Team City/Jenkins)
Pupet installation and setup
Puppet integration with CI Tool (Team City/Jenkins)
Docker installation and setup
Docker integration with CI Tool (Team City/Jenkins)
Setp RunDeck
Rundeck integration with CI tools
Jmeter Integration with CI Tool (Team City/Jenkins)
Integrate Release Managemt tools (Jira/XL Release/Plutora) with CI Tool (Team City/Jenkins)
Servicenow integration with RM and CI tools
Servicenow integration with RM and CD tools
Splunk/M360 integration
Jira and ServiceNow integration
3 | Build
Sub tasks | Code Review, Code coverage
Build Automation strategy
Configuring Auto builds
Unit Test
4 | Gating Standard - Sonar/Rspec(For Ruby)
Sub tasks | Install Sonar server
Configure Sonarqube runner
Enable static analysis with each build
Create/Configure quality gates
Install and configure Sonar plugins
Enable quality gates to reject the builds in case of major violations
Auto Publish of the Analysis report to Sonar Dashboard
Configure Sonar with Unit test folder for AngularJS
For Ruby need to integrate with Karma/Rspec/Rubycmp
5 | Integrated Test Automation | Mahantesh
6 | Binary repo - Nexus implementation
Install Nexus
Security model for the repository
Configure Nexus
Nexus/Maven Plugin implementation
Test Repo
7 | Environment management
Sub tasks | PCF
Firewall
8 | Config Automation
Sub tasks | Chef/Puppet/Ansible setup and configuration
9 | CD - Deployment Automation - Jmeter
Sub tasks | Setup Puppet/Linux/Bosh server and the manifest
Provision Firewall/PCF settings
Provision PCF Organization
Validate Jenkins/Concourse integration with PCF
Provision Environments (Test/Dev/Performance/UAT/QA)
Create API repository for Microservices
Systems Acceptance Testing ( Sign Off)
10 | Release Automation
Sub tasks | Need to select tool in workshop
Identify Tool chain integration
Acquire License
Install Backend (Mongo DB/Mysql) service
Decide on the tool Plutora/Udeploy in workshop
11 | Traceability metrics, KPI
Sub tasks | Establish baseline metrics for application(code quality/coverage/no. of builds per cycle)
Dashboard(OneDevops) and Infrastructure
Determine where the telemetry data is going to be stored
What data is involved
Deploy Splunk Enterpsise Agents/New Relic on Endpoints
HP ALM
Integrate Taskforce Jira and PCT
Integrate HP ALM
Integrate One Devops/Jira
Actively monitor performance over time
12 | Implement Insights
Sub tasks | Insights/M360/New Relic/Splunk
Validate the data in Monitoring tool - Insights
Validate data for Automation and Infrastructure Monitoring
Dashboard and Alerts with Role-based access to leverage performance, Infra and business metrics
Enable decision making based on specific alerts and metrics
13 | SCM/Git Repository Standardization
Sub tasks | Setup Git (Hosted/On Prem)
Create RBAC - Users, SVC account
Establish Best Practices Branching/Merging strategy for Code Review
Integrate with LDAP/SSON
Integrate with CI - Set up Webhooks, push-pull
Strategize build trigger, Code check-in
Integrate static code analysis, gating rules
14 | Jenkins Setup – CI Tool Implementation
Normalize pipeline based on dev stack(Ruby, Java, C#) - Separate Jenkins?
Sub tasks | Install Jenkins
Configure Jenkins
Plugin setup/Docker Installation/Junit/Karma
Define authorization strategy
Configuration and test the Jenkins Slave setup with Dev server
Configuration and test the Jenkins Slave setup with UAT/QA server
Create RBAC in Jenkins, Integrate SVC accounts
Get list of Active Jobs and verify current scripts being used
Get list of Active Jobs in DEV and QA for Applications ---
Email SMTP server details and setup Email notification
Integrate Git with Jenkins
Integrate Automated Build feature
Integrate Unit test and Reporting (Sonar)
Integrate & test Binary Repo(Nexus/Artifactory)
Integrate Deployment Scripts/Tools
15 | Docker Installation
Sub tasks | Configure pull Docker images
Configure Docker Registry
Setup RUN Docker Containers
Integrate Images to Docker Cloud for Deployment
Integrate Docker with Cloud hosts
16 | Sonar Ruby Plugin
Sub tasks | Install Sonar-Ruby Plugins
POC to enable Sonar analysis for Ruby projects
POC to capture basic code quality metrics
17 | Release management Tool Implementation
Sub tasks | Setup & Install tool in the platform
Configure RM tool with CI Tool (Jenkins/teamcity)
Define Integration of RM tool with SCM and ALM
Define Integration of RM with SNOW
Define Release Governance with gating
Setup RBAC - Define release activities and map roles
Test the Integration of RM tool in the pipeline
Setup Orchestration process with RM Tool
Define Audit Trials and Change Management integration in RM